## Deployment_scn_1
Month | Calendar | Subs | Crews | Weather | Installed | Cumulative | %
1 | 2027-09-01 | 4 | 73 | 1 | 1452 | 1452 | 0.7
2 | 2027-10-01 | 4 | 147 | 1 | 2904 | 4356 | 2.2
3 | 2027-11-01 | 6 | 264 | 0.6 | 3136 | 7492 | 3.7
4 | 2027-12-01 | 6 | 308 | 0.6 | 3659 | 11151 | 5.6
5 | 2028-01-01 | 10 | 418 | 0.6 | 4966 | 16117 | 8.1
6 | 2028-02-01 | 10 | 484 | 0.6 | 5750 | 21867 | 10.9
7 | 2028-03-01 | 10 | 550 | 1 | 10890 | 32757 | 16.4
8 | 2028-04-01 | 10 | 550 | 1 | 10890 | 43647 | 21.8
9 | 2028-05-01 | 10 | 550 | 1 | 10890 | 54537 | 27.3
10 | 2028-06-01 | 10 | 550 | 1 | 10890 | 65427 | 32.7
11 | 2028-07-01 | 10 | 550 | 1 | 10890 | 76317 | 38.2
12 | 2028-08-01 | 10 | 550 | 1 | 10890 | 87207 | 43.6
13 | 2028-09-01 | 10 | 550 | 1 | 10890 | 98097 | 49
14 | 2028-10-01 | 10 | 550 | 1 | 10890 | 108987 | 54.5
15 | 2028-11-01 | 10 | 550 | 0.6 | 6534 | 115521 | 57.8
16 | 2028-12-01 | 10 | 550 | 0.6 | 6534 | 122055 | 61
17 | 2029-01-01 | 10 | 550 | 0.6 | 6534 | 128589 | 64.3
18 | 2029-02-01 | 10 | 550 | 0.6 | 6534 | 135123 | 67.6
19 | 2029-03-01 | 10 | 550 | 1 | 10890 | 146013 | 73
20 | 2029-04-01 | 10 | 550 | 1 | 10890 | 156903 | 78.5
21 | 2029-05-01 | 10 | 550 | 1 | 10890 | 167793 | 83.9
22 | 2029-06-01 | 10 | 550 | 1 | 10890 | 178683 | 89.3
23 | 2029-07-01 | 10 | 550 | 1 | 10890 | 189573 | 94.8
24 | 2029-08-01 | 10 | 550 | 1 | 10427 | 200000 | 100

## Deployment_scn_2
Month | Calendar | Subs | Crews | Weather | Installed | Cumulative | %
1 | 2027-09-01 | 4 | 73 | 1 | 1936 | 1936 | 1
2 | 2027-10-01 | 4 | 147 | 1 | 3872 | 5808 | 2.9
3 | 2027-11-01 | 6 | 264 | 0.6 | 4182 | 9990 | 5
4 | 2027-12-01 | 6 | 308 | 0.6 | 4879 | 14868 | 7.4
5 | 2028-01-01 | 10 | 418 | 0.6 | 6621 | 21490 | 10.7
6 | 2028-02-01 | 10 | 484 | 0.6 | 7667 | 29156 | 14.6
7 | 2028-03-01 | 10 | 550 | 1 | 14520 | 43676 | 21.8
8 | 2028-04-01 | 10 | 550 | 1 | 14520 | 58196 | 29.1
9 | 2028-05-01 | 10 | 550 | 1 | 14520 | 72716 | 36.4
10 | 2028-06-01 | 10 | 550 | 1 | 14520 | 87236 | 43.6
11 | 2028-07-01 | 10 | 550 | 1 | 14520 | 101756 | 50.9
12 | 2028-08-01 | 10 | 550 | 1 | 14520 | 116276 | 58.1
13 | 2028-09-01 | 10 | 550 | 1 | 14520 | 130796 | 65.4
14 | 2028-10-01 | 10 | 550 | 1 | 14520 | 145316 | 72.7
15 | 2028-11-01 | 10 | 550 | 0.6 | 8712 | 154028 | 77
16 | 2028-12-01 | 10 | 550 | 0.6 | 8712 | 162740 | 81.4
17 | 2029-01-01 | 10 | 550 | 0.6 | 8712 | 171452 | 85.7
18 | 2029-02-01 | 10 | 550 | 0.6 | 8712 | 180164 | 90.1
19 | 2029-03-01 | 10 | 550 | 1 | 14520 | 194684 | 97.3
20 | 2029-04-01 | 10 | 550 | 1 | 5316 | 200000 | 100
21 | 2029-05-01 | 10 | 550 | 1 | 0 | 200000 | 100
22 | 2029-06-01 | 10 | 550 | 1 | 0 | 200000 | 100
23 | 2029-07-01 | 10 | 550 | 1 | 0 | 200000 | 100
24 | 2029-08-01 | 10 | 550 | 1 | 0 | 200000 | 100

## Deployment_scn_3
Month | Calendar | Subs | Crews | Weather | Installed | Cumulative | %
1 | 2027-09-01 | 4 | 73 | 1 | 2420 | 2420 | 1.2
2 | 2027-10-01 | 4 | 147 | 1 | 4840 | 7260 | 3.6
3 | 2027-11-01 | 6 | 264 | 0.6 | 5227 | 12487 | 6.2
4 | 2027-12-01 | 6 | 308 | 0.6 | 6098 | 18586 | 9.3
5 | 2028-01-01 | 10 | 418 | 0.6 | 8276 | 26862 | 13.4
6 | 2028-02-01 | 10 | 484 | 0.6 | 9583 | 36445 | 18.2
7 | 2028-03-01 | 10 | 550 | 1 | 18150 | 54595 | 27.3
8 | 2028-04-01 | 10 | 550 | 1 | 18150 | 72745 | 36.4
9 | 2028-05-01 | 10 | 550 | 1 | 18150 | 90895 | 45.4
10 | 2028-06-01 | 10 | 550 | 1 | 18150 | 109045 | 54.5
11 | 2028-07-01 | 10 | 550 | 1 | 18150 | 127195 | 63.6
12 | 2028-08-01 | 10 | 550 | 1 | 18150 | 145345 | 72.7
13 | 2028-09-01 | 10 | 550 | 1 | 18150 | 163495 | 81.7
14 | 2028-10-01 | 10 | 550 | 1 | 18150 | 181645 | 90.8
15 | 2028-11-01 | 10 | 550 | 0.6 | 10890 | 192535 | 96.3
16 | 2028-12-01 | 10 | 550 | 0.6 | 7465 | 200000 | 100

## Parametros_scn_3
{:working-days 22,
:houses-per-crew-day 1.5,
:peak-crews 550,
:rain-reduction 0.4,
:rainy-months #{1 12 2 11},
:subcontractors
[{:id "A1", :type :A, :start 1}
{:id "A2", :type :A, :start 1}
{:id "B1", :type :B, :start 1}
{:id "A3", :type :A, :start 3}
{:id "B2", :type :B, :start 1}
{:id "A4", :type :A, :start 3}
{:id "B3", :type :B, :start 5}
{:id "A5", :type :A, :start 5}
{:id "B4", :type :B, :start 5}
{:id "B5", :type :B, :start 5}],
:start-month "2027-09",
:total-households 200000,
:efficiency 1.0,
:scenario/name "base",
:ramp-months 3,
:horizon-months 24,
:capacity-ratio 1.5}

## Parametros_scn_2
{:working-days 22,
:houses-per-crew-day 1.2,
:peak-crews 550,
:rain-reduction 0.4,
:rainy-months #{1 12 2 11},
:subcontractors
[{:id "A1", :type :A, :start 1}
{:id "A2", :type :A, :start 1}
{:id "B1", :type :B, :start 1}
{:id "A3", :type :A, :start 3}
{:id "B2", :type :B, :start 1}
{:id "A4", :type :A, :start 3}
{:id "B3", :type :B, :start 5}
{:id "A5", :type :A, :start 5}
{:id "B4", :type :B, :start 5}
{:id "B5", :type :B, :start 5}],
:start-month "2027-09",
:total-households 200000,
:efficiency 1.0,
:scenario/name "base",
:ramp-months 3,
:horizon-months 24,
:capacity-ratio 1.5}

## Parametros_scn_1
{:working-days 22,
:houses-per-crew-day 0.9,
:peak-crews 550,
:rain-reduction 0.4,
:rainy-months #{1 12 2 11},
:subcontractors
[{:id "A1", :type :A, :start 1}
{:id "A2", :type :A, :start 1}
{:id "B1", :type :B, :start 1}
{:id "A3", :type :A, :start 3}
{:id "B2", :type :B, :start 1}
{:id "A4", :type :A, :start 3}
{:id "B3", :type :B, :start 5}
{:id "A5", :type :A, :start 5}
{:id "B4", :type :B, :start 5}
{:id "B5", :type :B, :start 5}],
:start-month "2027-09",
:total-households 200000,
:efficiency 1.0,
:scenario/name "base",
:ramp-months 3,
:horizon-months 24,
:capacity-ratio 1.5}